## Activities
Project PAM | [6 empty] | Sec Ref #: S14-75-3DPrinter
Action Item List
Team Members:
| JPB | Jeffrey Burdick ME
| CWB | Chance Baker EE
| CWS | Casey Spencer EE
| DMO | Daniel Olsen CE
| NBT | Nathaniel Tyler ME
| NAL | Nick Lowman CE
# | Activity | Person(s) | Date Assigned | Date Due | New Due | Status | Comments
1899-12-31 | Complete Prezi | DMO | 2014-08-19 | 2014-08-28
1900-01-01 | Complete Script Drafts | CWS,JPB,CWB | 2014-08-26 | 2014-08-28
1900-01-02 | Create Attendance Sheet | CWB | 2014-08-26 | 2014-09-02
1900-01-03 | ECE Order Forms | NAL | 2014-08-26 | 2014-08-28
1900-01-04 | ME Part Order | JPB | 2014-08-26 | 2014-08-28
1900-01-05 | Software Mashup | DMO | 2014-08-26 | 2014-09-02
1900-01-06 | Firmware Mashup | NAL | 2014-08-26 | 2014-09-03
1900-01-07 | Update GitHub Pages | DMO, NBT | 2014-08-26 | 2014-09-02
1900-01-08 | Update Timeline | DMO | 2014-08-26 | 2014-08-28
1900-01-09 | Turn in N&E Statement | NAL | 2014-08-26 | 2014-08-27
1900-01-10 | Funding Letters | CWS, JPB | 2014-08-26 | 2014-08-27
1900-01-11 | Take new Team Photo | ALL | 2014-08-27 | 2014-08-27
1900-01-12 | Initial Models | JPB | 2014-08-28 | 2014-09-02
1900-01-13
1900-01-14 | Get Access to Spring D2L | ALL | 2014-08-28 | 2014-08-28
1900-01-15 | Bring in Macro Lense | JPB | 2014-08-28 | 2014-09-02
1900-01-16 | Get Projector | NAL | 2014-08-26 | 2014-09-03
1900-01-17
1900-01-18
1900-01-19
1900-01-20
1900-01-21
1900-01-22
1900-01-23
1900-01-24
1900-01-25
1900-01-26
1900-01-27
1900-01-28
1900-01-29
1900-01-30
1900-01-31
1900-02-01
1900-02-02
1900-02-03
1900-02-04
1900-02-05
1900-02-06
1900-02-07
1900-02-08
1900-02-09
1900-02-10
1900-02-11
1900-02-12
1900-02-13
1900-02-14
1900-02-15
1900-02-16
1900-02-17
1900-02-18
1900-02-19
1900-02-20
1900-02-21
1900-02-22
1900-02-23
1900-02-24
1900-02-25
1900-02-26
1900-02-27
1900-02-28
1900-03-01
1900-03-02
1900-03-03
1900-03-04