## Activities
Project PAM | [6 empty] | Sec Ref #: S14-75-3DPrinter
Action Item List
Team Members:
| JPB | Jeffrey Burdick ME
| CWB | Chance Baker EE
| CWS | Casey Spencer EE
| DMO | Daniel Olsen CE
| NBT | Nathaniel Tyler ME
| NAL | Nick Lowman CE
# | Activity | Person(s) | Date Assigned | Date Due | New Due | Status | Comments
1 | Complete Prezi Draft | DMO | 2014-08-19 | 2014-08-28 |  | Done
2 | Complete Prezi Script Draft | CWS | 2014-08-26 | 2014-08-28 | 2014-08-29 | Done | "Casey is bad at script writing" - Casey
3 | Create Attendance Sheet | CWB | 2014-08-26 | 2014-09-02 |  | Done
4 | Funding Letters | CWS, JPB | 2014-08-26 | 2014-08-27 |  | On Hold | Waiting on Kickstarter
5 | ECE Order Forms | NAL, DMO | 2014-08-26 | 2014-08-28 |  | Done
6 | ME Part Order | JPB | 2014-08-26 | 2014-08-28 |  | On Hold | Waiting to hear from ECE parts order
7 | Software Mashup | DMO | 2014-08-26 | 2014-09-02 |  | Done
8 | Firmware Mashup | NAL | 2014-08-26 | 2014-09-03 | 2014-09-11 | Done
9 | Update Timeline | DMO | 2014-08-26 | 2014-08-28 |  | Done
10 | Turn in N&E Statement | NAL | 2014-08-26 | 2014-08-27 |  | Done
11 | Get Projector | NAL | 2014-08-26 | 2014-09-03 |  | N/A | Projector not DLP
12 | Take new Team Photo | ALL | 2014-08-27 | 2014-08-27 |  | Done
13 | Initial Models | JPB | 2014-08-28 | 2014-09-02 |  | Done
14 | Get Access to Spring D2L | ALL | 2014-08-28 | 2014-08-28 |  | N/A | Not happening
15 | Bring in Macro Lense | JPB | 2014-08-28 | 2014-09-02 |  | Done
16 | Complete Prezi Final Draft | DMO | 2014-09-02 | 2014-09-09 |  | Done
17 | Complete Prezi Script Final Draft | CWS | 2014-09-02 | 2014-09-09 |  | Done
18 | Website Content Draft | DMO, CWS | 2014-09-02 | 2014-09-04 |  | Done
19 | Source Prelim Motion Sys | NAL, NBT, JPB | 2014-09-02 | 2014-09-04 |  | Done
20 | Generate UML | DMO | 2014-09-02 | 2014-09-04 |  | Canceled | Not worth it
21 | Learn Code | DMO | 2014-09-02 | 2014-09-04 | 2014-09-18
22
23 | Update Website Format | DMO | 2014-09-04 | 2014-09-09 |  | Done
24 | Update GitHub READMEs | DMO | 2014-09-04 | 2014-09-09 |  | Done
25 | Assemble Prelim Motor Board | NAL | 2014-09-04 | 2014-09-09 |  | Done
26 | Assemble Prelim Linear Motion Sys | JPB, NBT | 2014-09-04 | 2014-09-11 |  | Done
27 | Record Prezi | CWS | 2014-09-09 | 2014-09-11 | 2014-09-18 | 50%
28 | Model Renderings | DMO | 2014-09-09 | 2014-09-11 |  | Done | 14 hours to render
29 | Add Facebook Content | CWS | 2014-09-09 | 2014-09-11 | 2014-09-23
30 | Add Twitter Content | CWB | 2014-09-09 | 2014-09-11 | 2014-09-23
31 | Add Google+ Content | CWS | 2014-09-09 | 2014-09-11 | 2014-09-23
32 | Add Website Content | DMO, CWS, CWB | 2014-09-09 | 2014-09-09 | 2014-09-23
33 | List of Media Outlets | CWB | 2014-09-09 | 2014-09-09 | 2014-09-18 | Done
34 | Test Prelim Motor Control | NAL | 2014-09-09 | 2014-09-18 | 2014-09-25 |  | Waiting for NEMA motors
35 | Test Prelim Linear Motion Sys | JPB, NBT | 2014-09-11 | 2014-09-18 | 2014-09-25 |  | Waiting for #34
36 | Upload Prezi to Youtube | CWS | 2014-09-11 | 2014-09-11 | 2014-09-18
37 | Kickstarter Content | DMO, CWS | 2014-09-11 | 2014-09-11 | 2014-09-23 | 25%
38 | grbl h-bridge support | NAL | 2014-09-25 | 2014-10-16 |  | In Progress
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72