## Activities
Project PAM | [6 empty] | Sec Ref #: S14-75-3DPrinter
Action Item List
Team Members:
| JPB | Jeffrey Burdick ME
| CWB | Chance Baker EE
| CWS | Casey Spencer EE
| DMO | Daniel Olsen CE
| NBT | Nathaniel Tyler ME
| NAL | Nick Lowman CE
# | Activity | Person(s) | Date Assigned | Date Due | New Due | Status | Comments
1 | Complete Prezi | DMO | 2014-08-19 | 2014-08-28 |  | Done
2 | Complete Script Drafts | CWS,JPB,CWB | 2014-08-26 | 2014-08-28 | 2014-08-29 | 50% | "Casey is bad at script writing" - Casey
3 | Create Attendance Sheet | CWB | 2014-08-26 | 2014-09-02 |  | Done
4 | ECE Order Forms | NAL | 2014-08-26 | 2014-08-28
5 | ME Part Order | JPB | 2014-08-26 | 2014-08-28 | 2014-09-03 | 0%
6 | Software Mashup | DMO | 2014-08-26 | 2014-09-02
7 | Firmware Mashup | NAL | 2014-08-26 | 2014-09-03
8 | Update GitHub Pages | DMO, NBT | 2014-08-26 | 2014-09-02
9 | Update Timeline | DMO | 2014-08-26 | 2014-08-28 |  | Done
10 | Turn in N&E Statement | NAL | 2014-08-26 | 2014-08-27 |  | Late | Done
11 | Funding Letters | CWS, JPB | 2014-08-26 | 2014-08-27 |  | On Hold | Waiting for Prezi and Script
12 | Take new Team Photo | ALL | 2014-08-27 | 2014-08-27 |  | Done
13 | Initial Models | JPB | 2014-08-28 | 2014-09-02
14
15 | Get Access to Spring D2L | ALL | 2014-08-28 | 2014-08-28 |  | ? | Waiting on profs
16 | Bring in Macro Lense | JPB | 2014-08-28 | 2014-09-02
17 | Get Projector | NAL | 2014-08-26 | 2014-09-03
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64